## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Sivakumar Thevar
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-02-26
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | FindMyCampus
PROJECT ID
INTERN NAME | Sivakumar Thevar
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
A test strategy is a detailed plan for testing an application, outlining the items, features, types of testing, resources, schedule, and associated risks. It outlines the approach to be followed during testing and outlines the necessary resources and schedule. It provides guidance on how testing will be conducted, what needs to be accomplished, and the methodology to achieve it.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Functional testing of the application. Verification of user interactions, data retrieval, and display. Pagination is properly working or not. Compatibility testing across browsers (HTML, CSS, JS). API testing (Node.js, Express.js). Database testing (MySQL). Searchable through form and well-presented upon the search input.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Hardware Interfaces Load testing Website Security
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The primary objective of our test strategy is to ensure the quality, reliability, and functionality of the FindMyCampus application. The test objectives aim to verify website functionality, including user interactions, data retrieval, and display, to ensure they function normally in a real business environment.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Developer: Manage the whole project, Implement the test cases, Identify the bugs and fix it, Check to confirm whether the testing process is meeting specified requirements.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
WaterFall: Requirements are clearly defined and stated beforehand. In the waterfall model, you can begin with the next phase only once the previous phase is completed.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
System Testing: End-to-end testing of the entire application. Validate user flows, data retrieval, and interactions. Unit Testing: Validate individual components (e.g., JS functions, Express.js routes, forms). Integration Testing: Verify interactions between frontend and backend components and database. Ensure seamless communication between frontend and backend via API endpoints. Compatibility Testing: Ensure cross-browser compatibility (HTML, CSS, JS). Evaluate system responsiveness. Usability Testing: Assess user-friendliness, navigation, and overall user experience. API Testing: Validate API endpoints (Node.js, Express.js).
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bug triage is the process of assessing and prioritizing defects based on factors like severity, frequency, and risk. It helps determine which issues need immediate attention and which can wait. Developer investigates the code, identifies the issue, and fixes it by updating the code. It will be scheduled during or after development, test phase.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
The criteria that denote a successful completion of a test phase is when it pass all the test levels and test cases.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Here are the deliverables • Test Plan • Traceability Matrix
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
VSCode IDE, XAMPP SQL, Browser and Browser console
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Frontend: Browser: Chrome, Firefox, Edge, Safari. OS: Windows, macOS, Linux. Backend: Node.js environment. Express.js server. MySQL database.
ADDITIONAL COMMENTS
-
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Frontend | HTML, CSS, images and additional content like icons | 2024-04-11 | 2024-04-12 | Developer | PASSED | Ensure proper rendering
Frontend | HTML, CSS, JS, forms | 2024-04-11 | 2024-04-12 | Developer | PASSED | Ensure user interaction
Navbar | Proper navigation to web pages | 2024-04-11 | 2024-04-12 | Developer | PASSED | Display appropriate pages
Animation Effects | Check CSS is properly linked | 2024-04-11 | 2024-04-12 | Developer | PASSED | Ensure proper rendering
Backend | Node.js, Express.js | 2024-04-11 | 2024-04-12 | Developer | PASSED | Validate API endpoints, and error handling.
Database | MySQL | 2024-04-11 | 2024-04-12 | Developer | PASSED | Test data integrity, queries, and performance.
Database testing | Test the database is connected or not and retrieve data | 2024-04-11 | 2024-04-12 | Developer | PASSED | Ensure properly configured with backend. Validate data retrieval, and error handling.
College data Results on web pages | College data results are shown to user | 2024-04-12 | 2024-04-13 | Developer | PASSED | Proper api endpoints and ensure proper table is connected to retrieve data and database is connected
College data Results without form input on web page | College data results are shown without user input just viewing page | 2024-04-12 | 2024-04-13 | Developer | PASSED | Proper api endpoints and ensure proper table is connected to retrieve data
College data Results with form input on web page | College data results are shown with user input | 2024-04-12 | 2024-04-13 | Developer | PASSED | Proper api endpoints and ensure proper table is connected to retrieve data
College data Results on web page | On submit of form with no input on state | 2024-04-12 | 2024-04-13 | Developer | PASSED | Display required fields
College data Results on web page | If inappropriate input is given | 2024-04-12 | 2024-04-13 | Developer | PASSED | Display data not found
College data Results on web page | If data not found | 2024-04-12 | 2024-04-13 | Developer | PASSED | Display data not found
College data Results on web pages | College data results are shown to user as per their requirements | 2024-04-12 | 2024-04-13 | Developer | PASSED | Ensure proper table is connected and accurate data shown and validate sql queries.
Frontend | Verification of user interactions, data retrieval, and display. | 2024-04-13 | 2024-04-14 | Developer | PASSED | Ensure proper rendering, and user interaction.
Pagination | Pagination is properly working or not and their buttons | 2024-04-13 | 2024-04-14 | Developer | PASSED | Ensure per page 10 record is shown. Also ensure enable/disable button of prev and next btn.
Responsiveness | Compatibility testing across different devices | 2024-04-13 | 2024-04-14 | Developer | PASSED | Ensure proper rendering, responsiveness.
Application | Functional testing of the application | 2024-04-14 | 2024-04-15 | Developer | PASSED | Validate each component working properly
Application | Assess user-friendliness, navigation, and overall user experience | 2024-04-15 | 2024-04-16 | Developer | PASSED | Check all working properly
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.